## Project Overview
🏥 Green Valley Hospital — Project Overview
Generated: July 18, 2026 10:28 PM CST
Project Name | Green Valley Hospital Management System
Client | Green Valley Hospital
Project Type | Full-Stack Web Application
Tech Stack | Python (FastAPI) · React 19 (Vite + TypeScript) · SQLite · JWT Auth
Methodology | Agile Scrum — Daily Standups
Sprint | Sprint 1 — Visual Enhancement & Full-Stack Implementation
Sprint Start | July 18, 2026
Sprint Status | In Progress
Scrum Master | Sunny
Orchestrator | Akhil
PIPELINE STATUS
# | Stage | Agent | Status | Completion % | Notes
1 | Requirements Gathering | Lavanya | Completed | 100% | Section 6 Visual & UI Enhancement requirements written to docs/requirements.md
2 | System Architecture & Design | Sagar | Completed | 100% | docs/api-spec.md, docs/design.md, db/schema.sql updated with v1.1 changes
3 | Backend Implementation | Pavan | Completed | 100% | FastAPI endpoints updated: profile_photo_path, recent_articles, department response shape, seed data
4 | Frontend Implementation | Chintu | Completed | 100% | 1891 modules, 0 TypeScript errors. All Section 6 visual pages, components, CSS tokens implemented
5 | QA & Testing | Gopal | In Progress | 60% | Running automated tests against Section 6 acceptance criteria + core API tests
6 | DevOps & Deployment | Indra | Pending | 0% | Awaiting client go-ahead after QA passes
7 | Application Launch | — | Pending | 0% | Final sign-off required from client

## Agent Status
👥 Agent Status & Deliverables
Last Updated: July 18, 2026 10:28 PM CST
Agent | Role | Status | Files Changed / Created | Key Deliverables | Bugs / Notes | Completion
Lavanya | Requirements Analyst | Completed | docs/requirements.md | • Added Section 6 (Visual & UI Enhancement) with 21 subsections • Defined 12 QA acceptance criteria (AC-VI-1 to AC-VI-12) • Specified 22 image assets, CSS token set, icon assignments • Backend change notes for Pavan: profile_photo_path, recent_articles, dept response | None | 100%
Sagar | Solution Architect | Completed | docs/api-spec.md docs/design.md db/schema.sql | • Updated API spec: 5 endpoint changes + new Section 6 notes block • Added profile_photo_path to Doctor, cover_image_path to BlogArticle • Defined full-bleed layout strategy (page-root, no negative-margin) • Documented CSS token additions, image asset strategy, responsive breakpoints • Chose GET /public/home as source for recent_articles (no second API call) | None | 100%
Pavan | Backend Developer | Completed | src/backend/app/models.py src/backend/app/schemas.py src/backend/app/database.py src/backend/app/routers/public.py src/backend/app/routers/doctor.py src/backend/app/routers/patient.py src/backend/app/routers/staff.py db/seed/seed.py | • profile_photo_path added to Doctor model (nullable, idempotent ALTER) • GET /public/home → recent_articles array + featured_departments.first_doctor • GET /public/departments/{id}/doctors → {department, items} shape • profile_photo_path included in all doctor endpoints (public, doctor, patient, staff) • PATCH /api/doctor/me accepts profile_photo_path • Seed: 4 doctors with photo paths, 3 extra blog articles, Pediatrics/Neurology depts | None | 100%
Chintu | Frontend Developer | Completed | src/frontend/src/index.css src/frontend/index.html src/frontend/src/components/* (4 new) src/frontend/src/layouts/* src/frontend/src/pages/public/* (9 pages) src/frontend/src/pages/admin/* src/frontend/src/pages/patient/* src/frontend/src/pages/doctor/* src/frontend/src/pages/staff/* src/frontend/src/pages/lab/* src/frontend/public/images/* (28 SVG placeholders) | • Full CSS design token system (colors, shadows, radii, typography) • Inter font via Google Fonts, Lucide React icons installed • Logo, SkeletonBlock, PageError, BackToTopButton components • Emergency strip + 4-column footer + sticky nav with hamburger • Home: hero, stats counter animation, Why Choose Us, Specialists, Testimonials, Blog • About: timeline, facility gallery, mission/vision/values cards • Departments: hero + search filter + image cards • Doctor profile: two-column layout + booking CTA strip • Contact: split layout + map placeholder + success state • Auth: split-screen login/signup with icon inputs + password toggle • All dashboards: sidebar icons, user block, topbar, skeleton loaders • Build: 1891 modules, 0 TypeScript errors, 799ms | None — clean build | 100%
Gopal | QA Engineer | In Progress | tests/* (new test files) docs/qa-report.md | • Running existing test suite • Writing new tests: Section 6 backend endpoint shapes • Writing tests: auth, patient isolation, doctor-patient RBAC, lab workflow • Generating QA report to docs/qa-report.md | TBD — in progress | 60%
Indra | DevOps Engineer | Pending | — | • Wire up run scripts for backend + frontend • Seed database and verify app boots end-to-end • Confirm all API endpoints reachable • Verify image assets served correctly | Awaiting client go-ahead | 0%

## Daily Scrum Log
📋 Daily Scrum Log — Green Valley Hospital
Managed by Sunny (Scrum Master) · 9am standup & 5pm update every weekday
Date | Standup | Agent | Yesterday / Plan | Today's Plan / Completed | Blockers | Status
Jul 18, 2026 | Morning (9am) | Lavanya | Sprint kick-off | Gather all visual & UI enhancement requirements for the website. Define image strategy, color tokens, icon system, page-by-page redesign specs, and backend change notes. | None | Completed
Jul 18, 2026 | Evening (5pm) | Lavanya | — | ✅ Completed Section 6 of docs/requirements.md — 21 subsections covering all UI enhancements, 12 QA acceptance criteria, 22 image asset specs, CSS token additions, icon mapping table, backend change notes for Pavan. | None | Completed
Jul 18, 2026 | Morning (9am) | Sagar | Requirements from Lavanya received | Design system architecture. Update API spec for profile_photo_path and dept response shape. Produce docs/design.md with layout strategy and component hierarchy. | None | Completed
Jul 18, 2026 | Evening (5pm) | Sagar | — | ✅ Updated docs/api-spec.md (5 endpoint changes + notes block). ✅ Added profile_photo_path to db/schema.sql. ✅ Created docs/design.md (16 sections) with full-bleed layout approach, CSS token spec, responsive breakpoints, image strategy. | None | Completed
Jul 18, 2026 | Morning (9am) | Pavan | Design artifacts from Sagar received | Implement all backend changes: profile_photo_path on Doctor model, recent_articles on home endpoint, department object in dept-doctors endpoint, update all doctor endpoints. | None | Completed
Jul 18, 2026 | Morning (9am) | Chintu | Design artifacts from Sagar received | Implement all frontend visual enhancements per Section 6. CSS tokens, icons, all public pages, auth pages, all dashboards, shared components, image placeholders. | None | Completed
Jul 18, 2026 | Evening (5pm) | Pavan | — | ✅ 8 files updated. Doctor model gains profile_photo_path. All 6 doctor-related endpoints updated. Home endpoint returns recent_articles. Dept-doctors returns {department, items}. Seed data updated with 4 doctors + photo paths + 3 blog articles. | None | Completed
Jul 18, 2026 | Evening (5pm) | Chintu | — | ✅ Build clean: 1891 modules, 0 TypeScript errors, 799ms. All 20+ pages redesigned. 4 new components. 28 SVG image placeholders. Full CSS token system. Lucide icons throughout. Counter animations, hamburger nav, split-screen auth, skeleton loaders, empty states. | None | Completed
Jul 18, 2026 | Morning (9am) | Gopal | Pavan + Chintu implementation complete | Run existing test suite. Write new tests for Section 6 backend changes and core acceptance criteria. Generate QA report. | None | In Progress

## Deliverables
📦 Project Deliverables
All files, documents, and artifacts produced in this sprint
Category | File / Artifact | Owner | Status | Description
Documentation | docs/requirements.md | Lavanya | Completed | Full functional requirements including Section 6 visual UI enhancements
Documentation | docs/api-spec.md | Sagar | Completed | REST API specification with all endpoint schemas (v1.1)
Documentation | docs/design.md | Sagar | Completed | System architecture, component hierarchy, CSS strategy, layout decisions
Documentation | docs/architecture.md | Sagar | Completed | High-level system architecture overview
Documentation | docs/data-dictionary.md | Sunny | Completed | All 16 database entities with column descriptions
Documentation | docs/developer-guide.md | Sunny | Completed | Setup, installation, running, seeding, demo accounts, troubleshooting
Documentation | docs/user-guide.md | Sunny | Completed | Role-by-role feature walkthroughs for all 5 roles + public site
Documentation | docs/security.md | Sunny | Completed | JWT auth, RBAC, access control matrix, password policy, out-of-scope items
Documentation | docs/qa-report.md | Gopal | In Progress | QA test results and bug log
Documentation | docs/scrum-tracker.xlsx | Sunny | Completed | This file — daily scrum log, agent status, pipeline tracker
Database | db/schema.sql | Sagar | Completed | Canonical DDL (v1.1): added profile_photo_path to doctors, cover_image_path to blog_articles
Database | db/seed/seed.py | Pavan | Completed | Idempotent seed: 4 doctors with photo paths, 8 departments, 3 blog articles, all roles
Backend | src/backend/app/models.py | Pavan | Completed | SQLAlchemy models — Doctor gains profile_photo_path
Backend | src/backend/app/schemas.py | Pavan | Completed | Pydantic schemas — DoctorUpdateMeRequest accepts profile_photo_path
Backend | src/backend/app/database.py | Pavan | Completed | init_db with idempotent ALTER TABLE migration
Backend | src/backend/app/routers/public.py | Pavan | Completed | Home returns recent_articles; dept-doctors returns {department, items}
Backend | src/backend/app/routers/doctor.py | Pavan | Completed | GET/PATCH /doctor/me include profile_photo_path
Backend | src/backend/app/routers/patient.py | Pavan | Completed | GET /patients/doctors includes profile_photo_path
Backend | src/backend/app/routers/staff.py | Pavan | Completed | GET /staff/directory includes profile_photo_path
Frontend | src/frontend/src/index.css | Chintu | Completed | Full design token system, all component styles, responsive breakpoints
Frontend | src/frontend/index.html | Chintu | Completed | Inter font via Google Fonts preconnect
Frontend | src/frontend/src/components/Logo.tsx | Chintu | Completed | SVG logo mark — default and white variants
Frontend | src/frontend/src/components/SkeletonBlock.tsx | Chintu | Completed | Shimmer loading skeleton — replaces all plain 'Loading...' text
Frontend | src/frontend/src/components/PageError.tsx | Chintu | Completed | Error card with AlertCircle icon and retry button
Frontend | src/frontend/src/components/BackToTopButton.tsx | Chintu | Completed | Floating back-to-top button with ChevronUp icon
Frontend | src/frontend/src/layouts/PublicLayout.tsx | Chintu | Completed | Emergency strip, Logo, hamburger menu, 4-column footer
Frontend | src/frontend/src/layouts/AppShell.tsx | Chintu | Completed | Sidebar with icons, user block, Bell topbar
Frontend | src/frontend/src/pages/public/HomePage.tsx | Chintu | Completed | Hero, stats counter, Why Choose Us, Specialists, Testimonials, Blog posts
Frontend | src/frontend/src/pages/public/AboutPage.tsx | Chintu | Completed | Page hero, timeline, facility gallery, mission/vision/values
Frontend | src/frontend/src/pages/public/DepartmentsPage.tsx | Chintu | Completed | Page hero, search filter, image cards with fallback
Frontend | src/frontend/src/pages/public/DoctorProfilePage.tsx | Chintu | Completed | Two-column layout, booking CTA strip
Frontend | src/frontend/src/pages/public/ContactPage.tsx | Chintu | Completed | Split layout, icon info cards, map placeholder, success state
Frontend | src/frontend/src/pages/public/LoginPage.tsx | Chintu | Completed | Split-screen, icon inputs, Eye/EyeOff password toggle
Frontend | src/frontend/src/pages/public/SignupPage.tsx | Chintu | Completed | Split-screen, patient-only info banner, icon inputs
Frontend | src/frontend/src/pages/admin/AdminDashboardPage.tsx | Chintu | Completed | Stat cards with icons + color borders + quick actions
Frontend | src/frontend/public/images/ (28 SVGs) | Chintu | Completed | Placeholder images for heroes, facilities, departments, doctors
.claude/agents/sunny.md | Agent Definition | Akhil | Completed | Sunny scrum master agent definition
docs/generate_tracker.py | Script | Sunny | Completed | Python script that regenerates this Excel tracker

## Bugs & Issues
🐛 Bugs & Issues Log
Logged by Gopal (QA). Updated after each test run.
ID | Date Found | Severity | Component | Description | Status | Assigned To
INFO-001 | Jul 18, 2026 | Info | Pipeline | Pavan and Chintu agents hit API session limit mid-work and were resumed. No data loss — both resumed cleanly from their transcript. | Resolved | Akhil